Start = 0-0 wk
Items = 1-2 wk
Clients = 1-3
Cart = 4-6
Catalog = 3-6
Order = 3-4
Payment = 4-6
Sort Items = 7-8
Add Items To Cart = 7-7
Place Order = 7-8
Pay Order = 7-8
GUI : Show item pages = 9-11
Cancel Order = 9-9
Admin : Retrieve Orders = 9-11
Admin : Change Order = 9-10
Show Popular Items = 12-14
Admin : Get Stats = 12-14
Finishing = 15-16

Critical Path :
Start – Clients – Payment – Retrieve Orders – Show Pop Items / Get Stats – Finishing
Start – Clients – Cart – Place Order – Retrieve Orders – Show Pop Items / Get Stats – Finishing
Start – Items – Catalog – Sort Items- Show item pages – Show Pop Items - Finishing