## ganttAssignment_(a)
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35					Juniors			Seniors
Start					Start		1			2
				Items		1			1
Items					Clients		1			1
				Catalog		1			2
Clients					Cart		1			1
				Order		0			2
Catalog					Payment		1			2
				Sort Items		1			0
Cart					Add Items to Cart		2			0
				Place Order		1			1
Order					Pay Order		1			2
				Gui: Show Item Page		2			2
Payment					Cancel Order		0			1
				Admin: Retrieve Orders		1			0
Sort Items					Admin: Change Order		1			1
				Show Popular Items		1			2
Add Items to Cart					Admin: Get Stats		1			0
				Finishing		2			1
Place Order

Pay Order

Gui: Show Item Page

Cancel Order

Admin: Retrieve Orders

Admin: Change Order

Show Popular Items

Admin: Get Stats

Finishing

Senior Staff

Junior Staf

Max 3 jun, 3 sen

## ganttAssignment_(b)
	1	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35					Juniors			Seniors
Start					Start		1			2
				Items		1			1
Items					Clients		1			1
				Catalog		1			2
Clients					Cart		1			1
				Order		0			2
Catalog					Payment		1			2
				Sort Items		1			0
Cart					Add Items to Cart		2			0
				Place Order		1			1
Order					Pay Order		1			2
				Gui: Show Item Page		2			2
Payment					Cancel Order		0			1
				Admin: Retrieve Orders		1			0
Sort Items					Admin: Change Order		1			1
				Show Popular Items		1			2
Add Items to Cart					Admin: Get Stats		1			0
				Finishing		2			1
Place Order

Pay Order

Gui: Show Item Page

Cancel Order

Admin: Retrieve Orders

Admin: Chagne Order

Show Popular Items

Admin: Get Stats

Finishing

Senior Staff

Junior Staf